## Open POA&M Items
FedRAMP® Plan of Action and Milestones (POA&M)
CSP | System Name | Impact Level | POAM Date
DCC IT Department. | DCC Network Infrastructure | Moderate | 2024-07-15
POAM ID | Controls | Weakness Name | Weakness Description | Weakness Detector Source | Weakness Source Identifier | Asset Identifier | Point of Contact | Resources Required | Overall Remediation Plan | Original Detection Date | Scheduled Completion Date | Planned Milestones | Milestone Changes | Status Date | Vendor Dependency | Last Vendor Check-in Date | Vendor Dependent Product Name | Original Risk Rating | Adjusted Risk Rating | Risk Adjustment | False Positive | Operational Requirement | Deviation Rationale | Supporting Documents | Comments | Auto-Approve | Binding Operational Directive 22-01 tracking | Binding Operational Directive 22-01 Due Date | CVE | Service Name
POAM-001 | AC.2.007 | No MFA for CUI systems | Lack of Multi-Factor Authentication (MFA) for systems handling CUI. | Security Assessment Report | N/A | All systems containing CUI (172.16.0.0/16) | John Doe - IT Security Team | MFA software, Training materials | Update Access Control Policy to mandate MFA, deploy MFA solutions, conduct MFA training. | 2024-07-15 | 2024-10-15 | (1) 2024-08-15: Policy Update ¦ (2) 2024-09-15: MFA Deployment ¦ (3) 2024-10-15: Staff/User Training | (2) Update 2024-09-18: Deployment delayed due to software issues | 45553 | No | N/A | N/A | High | Moderate | Yes | No | No | N/A | N/A | Training Records: MFA_Training.doc |  | No | No | N/A | N/A
POAM-002 | IR.2.093 | Outdated IRP | Incident Response Plan lacks comprehensive procedures for incident handling. | Security Assessment Report | N/A | IT Incident Response Documentation | Jane Smith - Incident Response Team | Staff time, Training materials | Revise IRP to include comprehensive procedures, conduct a tabletop exercise to validate new IRP. | 2024-07-15 | 2024-09-15 | (1) 2024-08-15: IRP Revision ¦ (2) 2024-09-15: Tabletop Exercise | (2) New 2024-08-18: Added additional exercise for validation | 2024-08-18 | No | N/A | N/A | Moderate | Low | Yes | No | No | N/A | N/A | Updated IRP: IRP_v2.doc |  | No | No | N/A | N/A
POAM-003 | AU.2.042 | Inadequate Logging | Minimal logging performed, no automated log analysis tools. | Nessus | 123456 | All network infrastructure (192.168.1.1/24) | Michael Lee - IT Security Team | Log Analysis Tools, Training | Enhance logging capabilities, implement automated log analysis tools, establish log review schedule. | 2024-07-15 | 2024-09-15 | (1) 2024-08-01: Log Configuration ¦ (2) 2024-09-01: Log Analysis Tool Deployment |  | 2024-08-01 | No | N/A | N/A | High | Moderate | Yes | No | No | N/A | N/A | Log Review Schedule: Log_Schedule.doc |  | No | No | N/A | N/A
POAM-004 | CM.2.064 | No Change Management Policy | No formal Change Management Policy for documenting and controlling changes. | Security Assessment Report | N/A | All IT systems | Sarah Jones - IT Operations Team | Change Management Tool, Policy Drafting | Develop a formal Change Management Policy, implement change management tool. | 2024-07-15 | 2024-10-15 | (1) 2024-08-15: Policy Development ¦ (2) 2024-10-15: Tool Implementation | (2) Update 2024-09-25: Tool delayed due to vendor dependency | 2024-09-25 | Yes | 2024-09-15 | Change Management Software | Moderate | Low | Yes | No | No | N/A | N/A | Change Mgmt Policy: CM_Policy.doc |  | No | No | N/A | N/A
POAM-005 | MP.2.120 | Unencrypted Data | Data not encrypted at rest and in transit, risking unauthorized access and data breaches. | Security Assessment Report | N/A | All databases and file storage systems (10.0.0.0/24) | David Brown - Compliance Team | Encryption Tools, Training | Develop Data Protection Policy mandating encryption, deploy encryption solutions for data at rest and in transit. | 2024-07-15 | 2024-11-15 | (1) 2024-08-15: Policy Development ¦ (2) 2024-11-15: Encryption Deployment |  | 2024-08-15 | No | N/A | N/A | High | High | Yes | No | No | N/A | N/A | Encryption Policy: Encryption_Policy.doc |  | No | No | N/A | N/A
POAM-006 | SC.2.171 | Insufficient Network Monitoring | Limited network security monitoring with no automated intrusion detection systems (IDS). | Nessus | 654321 | All network infrastructure (192.168.1.1/24) | Anna White - Network Security Team | Network Monitoring Tools, IDS | Deploy advanced network monitoring tools and IDS, configure automated alerts for potential threats. | 2024-07-15 | 2024-11-15 | (1) 2024-08-15: Tool Selection ¦ (2) 2024-11-15: Tool Deployment/Configuration |  | 2024-08-15 | No | N/A | N/A | High | Moderate | Yes | No | No | N/A | N/A | IDS Deployment Plan: IDS_Plan.doc |  | No | No | N/A | N/A
POAM-007 | CA.2.158 | Lack of Continuous Monitoring | No continuous monitoring strategy in place for cybersecurity controls. | Security Assessment Report | N/A | All IT systems | Tom Green - IT Operations & Security Teams | SIEM, Monitoring Tools | Develop a Continuous Monitoring Plan, deploy SIEM and integrate with IRP. | 2024-07-15 | 2024-10-15 | (1) 2024-08-15: Monitoring Plan Development ¦ (2) 2024-10-15: SIEM Deployment |  | 2024-08-15 | No | N/A | N/A | Moderate | Low | Yes | No | No | N/A | N/A | Monitoring Plan: Monitoring_Plan.doc |  | No | No | N/A | N/A
POAM-008 | RA.2.141 | Outdated Risk Assessment | Last risk assessment was three years ago, no ongoing risk management process. | Risk Management Tools | N/A | All IT systems | Emily Black - Risk Management Team | Risk Assessment Tools, Training | Conduct a comprehensive risk assessment, establish a continuous risk monitoring process. | 2024-07-15 | 2024-08-15 | (1) 2024-08-01: Risk Assessment ¦ (2) 2024-09-01: Continuous Monitoring Setup |  | 2024-08-01 | No | N/A | N/A | High | Moderate | Yes | No | No | N/A | N/A | Risk Assessment Report: Risk_Assessment.doc |  | No | No | N/A | N/A
POAM-009 | PE.2.131 | Limited Physical Security | Physical access to critical systems is restricted, but monitoring is minimal. | Physical Security Assessment | N/A | Data Center, Server Rooms | Mark Taylor - Facilities Management | Surveillance Cameras, Access Control Systems | Enhance physical security with additional surveillance and access controls. | 2024-07-15 | 2024-10-15 | (1) 2024-08-15: Security Assessment ¦ (2) 2024-10-15: Installation/Configuration |  | 2024-08-15 | No | N/A | N/A | Moderate | Low | Yes | No | No | N/A | N/A | Physical Security Report: Physical_Security.doc |  | No | No | N/A | N/A
POAM-010 | PS.2.134 | Inadequate Personnel Monitoring | No continuous monitoring or reassessment of personnel with access to CUI. | HR Review | N/A | All personnel with CUI access | Susan Grey - HR & Security Teams | HR System, Security Monitoring Tools | Establish continuous monitoring and reassessment processes for personnel. | 2024-07-15 | 2024-09-15 | (1) 2024-08-01: Policy Update ¦ (2) 2024-09-01: Process Implementation |  | 2024-08-01 | No | N/A | N/A | Moderate | Low | Yes | No | No | N/A | N/A | Personnel Monitoring Policy: Personnel_Policy.doc |  | No | No | N/A | N/A
POAM-011 | AT.2.056 | Insufficient Cybersecurity Training | Annual training lacks focus on CUI handling and advanced persistent threats (APTs). | Training Assessment | N/A | All IT staff | Lisa Kim - Training Coordinator | Training Software, Training Materials | Develop new training modules focusing on CUI handling and APT awareness, increase training frequency. | 2024-07-15 | 2024-09-15 | (1) 2024-08-01: Module Development ¦ (2) 2024-09-01: Training Rollout |  | 2024-08-01 | No | N/A | N/A | Moderate | Low | Yes | No | No | N/A | N/A | Training Program: Cyber_Training.doc |  | No | No | N/A | N/A

## Closed POA&M Items
FedRAMP Plan of Action and Milestones (POA&M) Template
CSP | System Name | Impact Level | POAM Date
Text | Text | Low | Date
POAM ID | Controls | Weakness Name | Weakness Description | Weakness Detector Source | Weakness Source Identifier | Asset Identifier | Point of Contact | Resources Required | Overall Remediation Plan | Original Detection Date | Scheduled Completion Date | Planned Milestones | Milestone Changes | Status Date | Vendor Dependency | Last Vendor Check-in Date | Vendor Dependent Product Name | Original Risk Rating | Adjusted Risk Rating | Risk Adjustment | False Positive | Operational Requirement | Deviation Rationale | Supporting Documents | Comments | Auto-Approve | Binding Operational Directive 22-01 tracking | Binding Operational Directive 22-01 Due Date | CVE | Service Name

## Configuration Findings
FedRAMP Plan of Action and Milestones (POA&M) Template
CSP | System Name | Impact Level | POAM Date
Text | Text | Low | Date
POAM ID | Controls | Weakness Name | Weakness Description | Weakness Detector Source | Weakness Source Identifier | Asset Identifier | Point of Contact | Resources Required | Overall Remediation Plan | Original Detection Date | Scheduled Completion Date | Planned Milestones | Milestone Changes | Status Date | Vendor Dependency | Last Vendor Check-in Date | Vendor Dependent Product Name | Original Risk Rating | Adjusted Risk Rating | Risk Adjustment | False Positive | Operational Requirement | Deviation Rationale | Supporting Documents | Comments | Auto-Approve | Binding Operational Directive 22-01 tracking | Binding Operational Directive 22-01 Due Date | CVE | Service Name

## Record of Changes
Record of Changes for Template
Date | Description | Version | Author
2023-08-30 | Updated to align with FedRAMP branding and minor editorial changes. | 2 | FedRAMP PMO
2024-03-29 | Added Tab for Configuration Findings. Added Column in 'Open POA&M' tab for Service level information | 2.1 | FedRAMP PMO